## 10 weeks WP
Task | Objective | Action | Duration | Deliverable
Build Updated Prototype | Develop and test an updated prototype using new chips (AD5761 for DAC, ADS1115 for ADC, TS5A3160 for analog switches) to verify functionality and ensure error-free PCB design. | Sourcing Components (Week 1, June 23–29): Prototype Assembly (Week 2, June 30 – July 6): Functional Testing (Week 3, July 7–14): Test potentiostat functionality (e.g., cyclic voltammetry). Validate performance against reference standards. Identify and resolve any issues with chip integration or circuit design. | 3 weeks (June 23 – July 14, 2025) | Fully functional updated prototype with verified performance.
PCB Design and Ordering | Design the PCB in EasyEDA and order 5 units for testing. | PCB Design (Week 4, July 15–21): Create schematic in EasyEDA incorporating AD5761, ADS1115, and TS5A3160. Layout PCB with proper routing, grounding, and noise reduction. Perform design rule check (DRC) and verify against prototype results. Order PCBs (Week 5, July 22–28): Export Gerber files and submit to JLCPCB (or similar) via EasyEDA. Order 5 PCBs with standard specifications (e.g., 2-layer, FR4). Confirm delivery timeline (typically 5–7 days). | 2 weeks (July 15–28, 2025) | PCB design files and 5 ordered PCBs.
Enclosure Design and Ordering | Design and order 5 enclosures for the pilot units. | Enclosure Design (Week 6, July 29 – August 4): Design enclosure in CAD software (e.g., Fusion 360 or FreeCAD) to fit PCB and components. Ensure access for ports, buttons, and display (if applicable). Select material (e.g., ABS plastic) for durability and cost-effectiveness. Order Enclosures (Week 7, August 5–11): Export design files (e.g., STL) and submit to manufacturing platform (e.g., Xometry or local 3D printing service). Order 5 enclosures, prioritizing cost and delivery speed. | 2 weeks (July 29 – August 11, 2025) | Enclosure design files and 5 ordered enclosures.
Improve Python GUI for Commercial Launch | Enhance the Python GUI for user-friendliness and commercial readiness. | GUI Design Update (Week 8, August 12–18): Review existing GUI for usability issues. Design intuitive interface with features like real-time data visualization, experiment setup, and data export. Use libraries like PyQt or Tkinter for cross-platform compatibility. Development and Testing (Week 9, August 19–25): Implement GUI improvements in Python. Ensure compatibility with updated hardware (e.g., communication with AD5761/ADS1115). Test GUI with prototype for reliability and responsiveness. Final Refinements (Week 10, August 26 – September 1): Incorporate user feedback from internal testing. Optimize performance and fix bugs. Package GUI for distribution (e.g., PyInstaller for executable). | 3 weeks (August 12 – September 1, 2025) | Commercial-ready Python GUI with documentation.